SFSPA Projects and Work Plans for the Intersessional Period

01 March 2010

|  | Workplan / expected outcome, deliverables | How (Key Activities/Actions) | Lead (bold) Members | Timelines | Associated meetings (discussion item in) | Resource Required for (apart from meetings) | ETs (bold)/ Linked With |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Develop a Guide to Operational Ocean Forecasting (Rec 8.1/1) | - (example) ET members provide input - (example) Consultant work to consolidate input | Gary Brassington … … | - ‘11 outline agreed - … - May‘12: intermediate outcome at JCOMM-IV | ETOOFS (?’) | (example) consultant contract | ETOOFS DMPA OPA |
| 2 | Define (assess) operational ocean observation requirements | - (example)Input from experts, to be agreed by SCG | Gary Brassington … … |  |  |  |  |
| 3 | Develop operational performance metrics to monitor operational ocean forecasts |  | Gary Brassington … … |  |  |  |  |
| 4 | User requirements for marine wx and oceanographic services - Conduct a joint survey (ETMSS, ETOOFS) on user requirements and service feedbacks | - Conduct a survey; - Analyze the response data | Gary Brassington Henri Savina … | - Dec’10 survey design agreed - ‘11 survey conducted - Mar’12 analysis on responses completed | ETMSS (Apr’10) ETOOFS(?) |  | ETOOFS, ETMSS |
| 6 | Address issues relating to the transition of a GODAE data service into operations |  | Gary Brassington … … |  |  |  |  |
| 7 | Facilitate implementation of Quality Management Systems (QMSs) for NOP among Members for the provision of Marine Accident Emergency Support |  | Gary Brassington … … |  |  |  | ETOOFS ETMSS |
| 8 | Developing an extreme wave database: - Establish a template for the extreme wave database - Establish the database at NOAA/ NODC | - Develop the template for extreme wave documentation (with ETMC) - Request input from countries, through OPA groups & Secretariat - Extending the DB to include satellite altimeter wave data | Val Swail | - May’10 template agreed, - Request input from countries (continue) | ETMC (Feb’10) ETWS (May’10) |  | ETWS, ETMC NOAA/NODC, DMPA groups |
| 9 | Assist ETMC to establish the SS climatology - A plan for S.S. climatology - A data base at host institution(s) | - Develop the plan with ETMC - Develop the SS climo. Database (with ETMC) | Val Swail | - ETMC (Feb’10) agree on the objectives - ETWS(2010) to decide on timeline - SSC2010 (Sep’10) discussion session on ongoing activities reSSclimatology - (date?) plan established | ETMC (Feb’10) ETWS (May’10) SSC2010 (Sep’10) |  | ETWS, ETMC LOICZ |
| 10 | Implement the recommendations from the 1st JCOMM SS Symposium: Support related S&T for a | - Support SSC2010 (JCOMM experts participation to organization & presentations) - Plan the 2nd SS Symposium | Val Swail Kevin Horsburgh Thomas Bruns | - Sep’10 SSC2010 discussion on SS climatology - May’12 approval on 2nd SS Symposium (after 2012) plan | ETWS (May’10) SSC2010 (Sep’10) | Expert participation to SSC2010 (external resources) | ETWS, ETMC LOICZ |
| 11 | Guide UNESCO pilot project on coastal hazard forecasting Establish action plans for the next phase of the project (expected outcome) | - SS Experts / ET members participation in NIO workshop - Review project progress in view of JCOMM work plan implementation | Kevin Horsburgh Val Swail Hans De Vries Don Resio | - May 10: ETWS meeting - Feb. 11: NIO workshop - Aug. 11: Action plan developed | ETWS (May’10) UNESCO NIO workshop (Feb’11) | Expert participation to NIO workshop (external resources: UNESCO/IOC) | ETWS, IOC/ICAM IIT (India) |
| 12 | Support JCOMM/CHy Coastal Inundation Forecast Demonstration Project |  | Val Swail Don Resio |  |  |  | ETWS WMO/CHy WMO/DRR |
| 13 | Facilitate the development of Storm Surge Watch Schemes (SSWS) for regions subject to tropical cyclones |  | Val Swail |  |  |  | ETWS |
| 14 | Support WMO Severe Weather Forecasting Demonstration Project (SWFDP) with respect to wave and storm surge issues |  | Val Swail Eugeny Nesterov |  |  |  | ETWS |
| 15 | Lead DBCP Pilot Projects on wave measurement evaluation and test (PP-WET) | - Review & update wave measurement requirements as necessary - Participate in, and provide guidance to intercomparison exercise & analysis | Val Swail Bob Jensen | - Jan’10 intercomparison website launch - Nov’10 PP 1st phase PP complete, plan for 2nd phase | PP SC (Feb’10) ETWS (May’10) DBCP26 (Sep’10) | Website development (external resources) | ETWS OPA/DBCP |
| 30 | Participate in the DBCP Pilot Project on wave measurement from drifters (PP-WMD) | - Review&update wave measurement requirements as necessary - Provide guidance as necessary | Val Swail Bob Jensen … | - Nov’10 PP 1st phase PP complete, plan for 2nd phase | ETWS (May’10) DBCP26 (Sep’10) |  | ETWS OPA/DBCP |
| 16 | Expansion of the Wave Forecast Verification Exchange Project in coordination with the ESA GlobWave project | - Review&update wave measurement requirements as necessary - ET members / experts participation | Val Swail Jean Bidlot |  | ETWS (May’10) |  | ECMWF ESA |
| 17 | Develop and update guidance documents | - Update wave guide by ET input + consultant work - Update dynamic part of SS guide as necessary (ET input) | Val Swail Thomas Bruns | - May’10 outline/contents of Wave guide agreed - May’12 Wave guide publication | ETWS (May’10) | WMO publication cost |  |
| 19 | Improve interaction between the GMDSS Issuing Services and AMOCs representatives of MPERSS | - create links to NMHC marine weather product websites for relevant METAREAS | Henri Savina … … |  |  |  | ETMSS |
| 20 | Keep under review the implementation of the GMDSS and MPERSS in the Arctic and continue to support the Issuing Services and AMOCs | - Experimental suite of on-demand Arctic marine/sea ice product – Text (PP) - Experimental suite of on-demand Arctic marine/sea ice product – Numerical/Graphical (PP) | Henri Savina Vasily Smolyanitky | - Apr’10 outline agreed - … - End’11 complete | ETSI (Mar’10) ETMSS (Apr’10) |  | ETMSS, ETSI, ETOOFS |
| 21 | In association with ETWS and ETSI, develop guidelines and recommendations to update WMO n°471 and 558, especially for the provision of sea state and sea ice in MSI |  | Henri Savina Val Swail Vasily Smolyanitky | - Mar’10 ETSI outline agreed - May’10 ETWS input provided - End’11 complete | ETSI (Mar’10) ETMSS (Apr’10) |  | ETMSS, ETWS ETSI |
| 22 | Continue to develop the catalogue on Met-Ocean Object Classes and Attributes to define standards for ENC and e-Navigation |  | Henri Savina Vasily Smolyanitky |  | ETSI (Mar’10) ETMSS (Apr’10) |  | ETMSS, ETSI, IMO, IHO |
| 23 | Facilitate implementation of Quality Management Systems (QMSs) among Members for the provision of MMS |  | Henri Savina … … |  |  |  |  |
| 24 | Update sea ice standards and climatology |  | Vasily Smolyanitky … … |  |  |  | ETSI, ETMC |
| 25 | Develop sea ice climatology based on ice charts and maintenance of the Global Digital Sea Ice Data Bank (GDSIDB) |  | Vasily Smolyanitky … … |  |  |  | ETSI |
| 26 | Contribute to the development and implementation numerical forecasting systems |  | Vasily Smolyanitky … … |  |  |  | ETOOFS |
| 27 | Enhance the efficiency and safety of navigation in ice infested waters by harmonizing sea ice products |  | Vasily Smolyanitky … … |  |  |  |  |
| 28 | Coordinate the implementation of GMDSS, including Sea Ice bulletins, for the Arctic Ocean | - MPERSS/GMDSS workshop (4/10) | Henri Savina Vasily Smolyanitky | - Complete by 2011 |  |  | ETMSS ETSI |
| 29 | Continue to develop and manage technical documentation for ENC and sea ice services and information |  | Vasily Smolyanitky … … |  |  |  |  |

Green – Project outcomes achieved by JCOMM-IV			White – Completion time line to be determined

Yellow – Possible to achieve the outcomes by JCOMM-IV		Blue – Lead by other PAs/Organizations

Table 2:	Capacity Building Projects

| 5 | Technology transfer/training on ocean forecasting systems | GODAE Summer School | Gary Brassington (ETOOFS) | Jan. 2010, Perth, Australia |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 18 | Capacity building on coastal hazard forecasting | North Indian Ocean SS workshop | Val Swail (ETWS), UNESCO | Feb. 2011 |  | S.S, experts (w/external resource) | WMO/VCP; IOC/IODE |
| 30 | Application of Satellite obs. | Training workshop in Brassels, Belgium | SFSPA, ESA | Dec. 2009 |  |  |  |
| 31 | Marine forecasting training | Training workshop in Dakar, Senegal | SFSPA (WMO), U.S. Navy, NOAA | April/May 2010 |  |  | WMO/VCP; |
|  | Support training series (WMO/VCP workshop, JCOMM/IODE Jamboree, etc) | Providing/updating training contents Providing lecturers/trainers |  |  |  |  |  |
| 32 | Sea Ice Analysis Training (COMET Modules) Outcomes: - Complete Module 1 (Sept. 10) - Input for Module 2 contents | Sea Ice analysis training module (#2) | ETSI (Caryn), AARI | - Review the course outline (module 1): April 10 - Sept 10 module 1 published - Input for module #2: April 10 |  |  |  |

Green – Project outcomes achieved by JCOMM-IV			White – Completion time line to be determined

Yellow – Possible to achieve the outcomes by JCOMM-IV		Blue – Lead by other PAs/Organizations